## Original Project Plan
Week | Python App | GitHub | Azure | Version
1 - 4 | Create Architecture Plan | Setup Repository | Setup Azure & Azure DevOps | 0.2
5 - 8 | Build App | Integrate CI | Create CD | 0.4
9 -12 | Test CI | Test CI & CD with Github Actions | Test CI & CD with Azure Pipelines | 0.6
12 - 16 | QA | QA | QA | 1

## Quarterly Plan
Week | Python App | GitHub | Azure | Version
2021-01-18 | Create Architectural Diagram | Create Repository | Create Azure & Azure DevOps Account | 0.1
2021-01-25 | Clone Artifacts & Create Build Workflow | Integrate GitHub Actions with Build Workflow | Create Resource Group & App Service Plan | 0.2
2021-02-01 | Test continuous Delivery | Test Continuous Integration | Create Azure Pipeline | 0.3
2021-02-08 | Develop Tests for Local Deployment | Develop Tests for Cloud Deployment | Develop Tests for Pipeline Deployment | 0.4
2021-02-15 | Develop Data Retrieval for ML App | Deploy app from GitHub Actions | Deploy App to Azure App Service | 0.5
2021-02-22 | Test Data Retrieval with Housing Data | Test Continuous Integration for ML app | Test Continuous Delivery for ML app | 0.6
2021-03-01 | Test Continuous Delivery for ML app | Test Continuous Delivery with GitHub Actions | Test Deployment to Azure App Service | 0.7
2021-03-08 | Perform Integration Testing | Perform Integration Testing | Perform Integration Testing | 0.8
2021-03-15 | Perform Integration Testing | Perform Integration Testing | Perform Integration Testing | 0.9
2021-03-22 | Load Test ML app (Locally) | Verify Deployment Correctness | Load Test ML app from Azure Websites | 1
2021-03-29 | App is ready for QA | QA Testing | QA Testing | 1
2021-04-05 | Deploy App to Production | QA Deployment | QA Deployment | 1
| Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1 -3 (1 easy and 3 tough) | Feature Category | Project Management Guidelines
| Develop Python App | Create Build Workflow | 3 | DevOps | Demo app every Monday
| Create Continuous Integration Workflow | Develop Tests for Local Deployment | 2 | Testing | Perform Weekly planning after Demo
| Create Continuous Deployment Workflow | Develop Tests for Cloud Deployment | 2 | Testing | Create a Release every 2 weeks
|  | Develop Tests for Pipeline Deployment | 2 | Testing & DevOps | Tickets represent 4 hour - 3 day block of work
|  | Continuous Delivery to GitHub | 1 | DevOps
|  | Continuous Integration with GitHub | 1 | DevOps
|  | Continuous Delivery with GitHub Actions | 1 | DevOps
|  | Continuous Delivery with Azure Pipelines | 1 | DevOps
|  | Load Test ML Python App | 2 | QA

## Yearly Plan
| Python App | GitHub | Azure | Version
Quarter 1 | Create Python & ML APP | Create Repository and Integrate CI | Create Azure & Azure DevOps Account & Integrate CD | 0.1
Quarter 2 | Deploy App to Docker & Kubernetes | Integrate Container Registry & Container Linting | Integrate Container Registry & App Service Plan | 0.2
Quarter 3 | Integrate Continuous API Testing | Integrate Continuous API Testing | Integrate Continuous API Testing | 0.3
Quarter 4 | Create CI & CD Process for Java Apps | Create CI & CD Process for Java Apps | Create CI & CD Process for Java Apps | 0.4